## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a new user, I want to be able to create an account, so that I can save my trip(s). | 1 | H | C | 3
2 | As a returning user, I want to be able to login to view my saved trip(s). | 1 | H | C | 2
3 | As a logged in user, I want to be able to see available flights, so that I can make the most cost and time effective trip possible. | Future Work | L | W | 4
4 | As a logged in user, I want to be able to find alternative flights if the one that I was going to take gets canceled, so that I can get to my destination as quickly as I can. | Future Work | L | W | 3
5 | As a logged in user, I want to be able to view hotels near my destination, so I can plan my night. | Future Work | L | W | 4
6 | As a logged in user, I want to be able to view restaurants near my destination, so I can find a place to eat. | 3 | H | W | 4
7 | As a logged in user, I want to be able to view local attractions near my destination, so I can find activities to do. | 3 | H | IP | 4
8 | As a logged in user, I want to be able to view reviews of places, so I can trust that I will enjoy my time. | 4 | H | W | 3
9 | As a logged in user, I want to be able to filter my search for places with criteria like price, so that I can go to places that best fit my needs. | 5 | L | IP | 3
10 | As a logged in user, I want to be able to view car rentals near my destination, so that I can find a private mode of transportation. | Future Work | L | W | 4
11 | As a logged in user, I want to be able to see available trains to my destination, so I can find a more environmentally conscious mode of transportation. | Future Work | L | W | 4
12 | As a logged in user, I want to be able to see available buses to my destination, so I can find a cheaper, more environmentally conscious mode of transportation. | Future Work | L | W | 4
13 | As a logged in user, I want to be able to save my planned routes, so I can access them more easily. | Future Work | L | W | 3
14 | As a logged in user, I want to know how long my planned routes will take, so I can plan that time into my day. | Future Work | L | W | 3
15 | As a logged in user, I want to be able to pay for flights through this app, so that I can do everything in one place. | Future Work | L | W | 5
16 | As a logged in user, I want to be able to pay for hotels through this app, so that I can do everything in one place. | Future Work | L | W | 5
17 | As a logged in user, I want to be able to pay for car rentals through this app, so that I can do everything in one place. | Future Work | L | W | 5
18 | As a logged in user, I want to be able to pay for train tickets through this app, so that I can do everything in one place. | Future Work | L | W | 5
19 | As a logged in user, I want to be able to pay for bus tickets through this app, so that I can do everything in one place. | Future Work | L | W | 5
20 | As a logged in user, I want to be able to pay for tickets to local attractions through this app, so that I can do everything in one place. | Future Work | L | W | 5
21 | As a logged in user, I want to be able to save payment information, so I can book places, flights, etc. more quickly and easily. | Future Work | L | W | 5
22 | As a logged in user, I want to have a travel log feature, so I can plan my day(s). | 1 | H | IP | 3
23 | As a logged in user, I want to be able to have multiple travel logs at once, so that I can plan multiple trips in advance. | 2 | H | IP | 3
24 | As a logged in user, I want to be able to remove travel logs, so it's not cluttered. | 2 | H | IP | 2
25 | As a logged in user, I want to be able to store documents associated with my travel log, such as reservation info or tickets for activities I've planned, so that I can have everything I need in one place. | 4 | H | W | 3
26 | As a logged in user, I want to be able to sync with my email to be able to access documents that have been emailed to me, so that I don't have to transfer the data myself. | Future Work | L | W | 4
27 | As a logged in user, I want to be able to store photos in my travel log, so that I can keep and organize my experiences for myself and others. | 3 | H | W | 3
28 | As a logged in user, I want to be able to store videos in my travel log, so that I can keep and organize my experiences for myself and others. | 5 | H | W | 3
29 | As a logged in user, I want to share my travel log, so others can know my plans. | Future Work | L | W | 4
30 | As a logged in user, I want to be able to add friends, so I can share my travel log. | Future Work | L | W | 4
31 | As a logged in user, I want to be able to share editing access of my travel log, so that I can plan a trip involving multiple people. | 5 | H | W | 3
32 | As a logged in user, I want to be able to create a budget for my trip, so that I can make financially responsible decisions. | Future Work | L | W | 4
33 | As a logged in user, I want to be able to enter expenses in any currency, so that I do not have to make conversions in order to enter information. | 4 | M | W | 3
34 | As a logged in user, I want to have a packing list feature, so that I can be assured that I have everything that I need. | 4 | M | W | 3
35 | As a logged in user, I want the packing list to be dynamic to match anticipated weather, so that I know that I am prepared for my trip. | Future Work | L | W | 5
36 | As a logged in user, I want the packing list to be dynamic to match planned activities, so that I know that I am prepared for my trip. | Future Work | L | W | 5
37 | As a logged in user, I want to be able to make other lists, such as grocery, to use during my trip, so I can keep track of what I need. | Future Work | L | W | 3
38 | As a logged in user, I want to be able to download my travel logs, so I can always access them, regardless of my wifi or data signal. | Future Work | L | W | 3
39 | As a logged in user, I want to be able to export my information as a spreadsheet, so I can store and share my information independently from the app. | 4 | M | W | 3
40 | As an administrator, I want to be able to view user accounts to help with troubleshooting. | Future Work | L | W | 4
41 | As an administrator, I want to be able to edit locations, so customers can have the most up to date information. | Future Work | L | W | 4
42 | As an owner/stockholder, I want users' personal information to be properly secured and encrypted, so that users' information is not stolen. | 3 | H | IP | 2
43 | As a guest user, I want to be able to view locations without an account, so there isn't any commitment. | Future Work | M | W | 2