## Sheet1
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a new user, I want to be able to create an account, so that I can save my trip(s). | -set environment | 1 |  | F | 3 | 2 | Jeffery (34%) ¦ Joe (66%)
-create sign-up screen
-add user + info to db
2 | As a returning user, I want to be able to login to view my saved trip(s). | -create log-in screen | 1 |  | F | 2 | 0 | Darien (100%)
-authenticate user's email and password
22 | As a logged in user, I want to have a travel log feature, so I can plan my day(s). | -research other examples of travel log/itinerary apps | 1 |  | F | 3 | 1 | Mary Isabelle (100%)
-create travel log page
-add functionality to allow user to manually enter plans
23 | As a logged in user, I want to be able to have multiple travel logs at once, so that I can plan multiple trips in advance. | -create page to view multiple trips | 2 |  | F | 3 | 0 | Sophie (100%)
-add db depencancies for multiple travel logs
-add functionality to add travel log
24 | As a logged in user, I want to be able to remove travel logs, so it's not cluttered. | -add functionality to delete travel log | 2 |  | F | 2 | 0 | Jeffery (100%)
42 | As an owner/stockholder, I want users' personal information to be properly secured and encrypted, so that users' information is not stolen. | -add encrytion to stored user information | 2 |  | NF: T | 2 | 0 | Mary Isabelle (100%)
6 | As a logged in user, I want to be able to view restaurants near my destination, so I can find a place to eat. | -connect to location information from google maps | 3 |  | F | 4 | 1 | Jeffery (100%)
-display information to user
7 | As a logged in user, I want to be able to view local attractions near my destination, so I can find activities to do. | -connect to location information from google maps | 3 |  | F | 4 | 0 | Sophie (100%)
-display information to user
27 | As a logged in user, I want to be able to store photos in my travel log, so that I can keep and organize my experiences for myself and others. | -add functionality to save photos to travel log | 3 |  | F | 3 | 0 | Joe (100%)
-display photos to user
8 | As a logged in user, I want to be able to view reviews of places, so I can trust that I will enjoy my time. | -find review service to connect to | 4 |  | F | 3 | 0 | Darien (100%)
-connect to review infromation
-display information to user
9 | As a logged in user, I want to be able to filter my search for places with criteria like price, so that I can go to places that best fit my needs. | -add ui for filtering search | 4 |  | F | 3 | 1 | Joe (100%)
-add functionality for filtering search
28 | As a logged in user, I want to be able to store videos in my travel log, so that I can keep and organize my experiences for myself and others. | -add functionality to save video to travel log | 4 |  | F | 3 | 0 | Mary (100%)
-display videos to user
31 | As a logged in user, I want to be able to share editing access of my travel log, so that I can plan a trip involving multiple people. | -add db dependancies for multiple users to a travel log | 4 |  | F | 3 | 0 | Sophie (100%)
-add functionality to share travel log to other users